## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
[5 empty] | Tursday | Thursday | Tuesday | Thursday | Tuesday | Thursday
Planning
UML Diagram |  | Kyle |  | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
JavaDoc |  | Kyle |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Task
Task
Modeling the Neighborhood
Street Class |  | Davin |  | 4 | 4 | 4 | 4 | 4 |  | 4 | 4
Neighborhood Class |  |  |  | 3 | 3 | 3 | 3 | 3 |  | 3 | 3
House Class |  |  |  | 3 | 3 | 3 | 3 | 3 |  | 3 | 3
Task
Neighborhood Gui
GUI |  | David |  | 5 | 3.5 | 3 | 3 | 3 |  | 3 | 3
Task
Task
Task
100 Random Addresses
Create Code |  | Max |  | 4 | 3 | 2 | 1 | 0 |  | 0 | 0
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 23 | 20.5 | 18 | 16 | 15 | 2 | 15 | 15

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0